## Sheet1
Game System | Task Description | Resource / Person | Best | Worst | Most Likely | result
Environmental Assets | [5 empty] | 0
Concept Art | Outline designs for envinmental assets (buildings ect). | RL | 1 | 6 | 3 | 3 | formula for end result= Best + x3 Worst + x2 Most Likely Divided by 6 = result
Modelling (Asset) | Polygon modelling of concept art | CD | 4 | 24 | 8 | 11.3333
UV unwrap | UV Unwrap of asset to pipeline specifications | CD | 1 | 8 | 4 | 3.8333
Texturing | Application of texturing workflows | CD | 1 | 10 | 3 | 4.3333 |  | K13(D3+(3*E3)+(2*F3))/6
Lightmap creation | Production of lightmaps for UE4 (UV set 2) | DD | 1 | 4 | 1 | 2
Engine Optimization | Importing and setup in engine | DD | 1 | 4 | 1 | 2
0
Player Character Asset | [5 empty] | 0
Concept Art | Outline designs for character | RL | 1 | 6 | 1 | 2.6667
Modelling | Polygon modelling of concept art | RL | 4 | 24 | 8 | 11.3333
UV Unwrap | UV Unwrap of asset to pipeline specifications | RL | 1 | 10 | 4 | 4.5
Texturing | Application of texturing workflows | CD | 1 | 10 | 4 | 4.5
Rigging | Application of rigging skeleton for animation | MH | 1 | 24 | 4 | 9.1667
Animation | Animating of the character | RL | 2 | 24 | 6 | 10
Engine Implementation | Importing and setup in engine | DD | 1 | 4 | 1 | 2
0
Props Assets | [5 empty] | 0
Concept Art | Outline designs for prop assets (furniture etc) | RL | 1 | 6 | 2 | 2.8333
Modelling | Polygon modelling of concept art | CD | 3 | 24 | 6 | 10.5
UV Unwrap | UV Unwrap of asset to pipeline specifications | CD | 2 | 24 | 6 | 10
Texturing | Application of texturing workflows | CD | 2 | 24 | 6 | 10
0
Programming - Interactables | [5 empty] | 0
UE4 research | Research of the required blueprints | DD | 1 | 12 | 3 | 5
Implementation | The implimentation of required blueprints | DD | 4 | 12 | 8 | 7.3333
Testing | Testing game for bugs. | DD | 1 | 6 | 2 | 2.8333
0
0
0
0
0
0
0